## Master Schedule
Task ID | Task Name | Location/Equipment | Duration (days) | Start Week | End Week | Responsible | Cost (USD) | Risk Level
1.1 | Preliminary Design | Design Office | 21 | 1 | 3 | Design Eng | 50000 | Low
1.2 | Detailed Design | Design Office | 14 | 3 | 5 | Design Eng | 40000 | Low
1.3 | Regulatory Permits & Approvals | Office/Authority | 28 | 1 | 5 | Project Manager | 15000 | Medium
2.1 | Material Procurement - Tanks & Equipment | Vendor | 35 | 2 | 7 | Procurement | 850000 | High
2.2 | Concrete & Reinforcement | Supplier | 21 | 4 | 7 | Procurement | 200000 | Medium
2.3 | Piping & Fittings | Supplier | 21 | 4 | 7 | Procurement | 120000 | Medium
2.4 | Electrical & Control Systems | Supplier | 28 | 3 | 7 | Procurement | 180000 | Medium
3.1 | Site Preparation & Survey | Site | 7 | 6 | 7 | Site Manager | 30000 | Low
3.2 | Piling Design Submission | Design/Engineer | 7 | 6 | 7 | Structural Eng | 20000 | Medium
3.3 | Piling Works | Site - Foundation | 21 | 7 | 10 | Piling Contractor | 250000 | High
3.4 | Excavation & Dewatering | Site | 14 | 8 | 10 | Excavation Contractor | 80000 | High
4.1 | Pile Cutting | Site - Foundation | 7 | 10 | 11 | Cutting Specialist | 40000 | High
4.2 | Pile Capping & Foundation | Site - Foundation | 14 | 11 | 13 | Concrete Contractor | 120000 | High
4.3 | Anchoring & Reinforcement | Site - Foundation | 14 | 11 | 13 | Steel Contractor | 100000 | High
4.4 | Formwork & Concrete Pour | Site - All Tanks | 35 | 12 | 17 | Concrete Contractor | 350000 | High
4.5 | Waterproofing - Floor & Walls | Site - All Tanks | 21 | 17 | 19 | Waterproofing Specialist | 150000 | Medium
4.6 | Curing & Quality Testing | Site | 14 | 17 | 19 | QC Engineer | 40000 | Medium
5.1 | Aeration Tank Installation | Site - Aeration | 14 | 19 | 21 | Equipment Installer | 120000 | High
5.2 | Clarifier Installation | Site - Clarifier | 14 | 20 | 22 | Equipment Installer | 100000 | High
5.3 | Sand Filter Installation (Triple) | Site - Filter | 21 | 20 | 23 | Equipment Installer | 180000 | High
5.4 | Chlorination System Installation | Site - Disinfection | 14 | 22 | 24 | Equipment Installer | 80000 | Medium
5.5 | EDI Filter Installation | Site - Polishing | 14 | 22 | 24 | Equipment Installer | 90000 | Medium
5.6 | Piping & Connections | Site - All | 21 | 20 | 23 | Piping Contractor | 140000 | High
5.7 | Electrical & Control Installation | Site - All | 21 | 21 | 24 | Electrical Contractor | 110000 | High
6.1 | System Pre-Commissioning Checks | Site | 7 | 24 | 25 | Commissioning Eng | 50000 | High
6.2 | Water Balance & Performance Testing | Site | 14 | 25 | 27 | Commissioning Eng | 60000 | High
6.3 | Staff Training & Handover | Site/Office | 7 | 26 | 27 | Project Manager | 35000 | Low
6.4 | Plant Startup & Optimization | Site | 14 | 27 | 29 | Operations Manager | 40000 | High